## Introduction
BIM Goals and BIM Uses Template Spreadsheet
The purpose of this worksheet is to assist project team members in the development of BIM Goals and the selection of BIM Uses based on project and team characteristics.
This template contains separate Worksheets (see the bottom of this window) for:
Goal Identification
Goal Examples
BIM Use Analsysis
BIM Uses Example

## 1a) Goal Identification
Project Goals
Priority | Project Goal | Potential BIM Uses
1 = Most Important

## Goal EXAMPLE
Project Goals (EXAMPLE)
Priority (1-3) | Project Goal | Potential BIM Uses
1= Most Important
1 | Ensure a high quality of design and design documentation | Design Authoring, Design Reviews, 3D Coordination
1 | Coordinate the transition of occupants into the building | 4D Modeling
2 | Increase the productivity of field installation | Design Reviews, 3D Coordination
2 | Accurately track the progress of construction | 4D Modeling
2 | Develop an accurate record of the final building design for use in future renovation projects | Record Model, 3D Coordination
1 | Achieve the sustainability targets | Engineering Analysis, LEED Evaluation
3 | Effectively monitor the progress of design to ensure target for construction start is achieved | Design Reviews
3 | Accurately review the cost impact of changes in a timely manner | Design Authoring, Cost Estimation

## 1b) BIM Use Analysis
BIM Use* | Value to Project | Responsible Party | Value to Resp Party | Capability Rating |  |  | Additional Resources / Competencies Required to Implement | Notes | Proceed with Use
| High / Med / Low |  | High / Med / Low | Scale 1-3 (1 = Low) |  |  |  |  | YES / NO / MAYBE
|  |  |  | Resources | Competency | Experience
Maintenance Scheduling
Building Systems Analysis
Record Modeling
Cost Estimation
4D Modeling
Site Utilization Planning
Layout Control & Planning
3D Coordination (Construction)
Engineering Analysis
Site Analysis
Design Reviews
3D Coordination (Design)
Existing Conditions Modeling
Design Authoring
Programming
* Additional information on each BIM Use can be found at http://bim.psu.edu or via the direct link by selecting each use

## BIM Use EXAMPLE
BIM Use* | Value to Project | Responsible Party | Value to Resp Party | Capability Rating |  |  | Additional Resources / Competencies Required to Implement | Notes | Proceed with Use
| High / Med / Low |  | High / Med / Low | Scale 1-3 (1 = Low) |  |  |  |  | YES / NO / MAYBE
|  |  |  | Resources | Competency | Experience
Record Modeling | HIGH | Contractor | MED | 2 | 2 | 2 | Requires training and software |  | YES
|  | Facility Manager | HIGH | 1 | 2 | 1 | Requires training and software
|  | Designer | MED | 3 | 3 | 3
Cost Estimation | MED | Contractor | HIGH | 2 | 1 | 1 |  |  | NO
4D Modeling | HIGH | Contractor | HIGH | 3 | 2 | 2 | Need training on latest software | High value to owner due to | YES
[7 empty] | Infrastructure needs | phasing complications
Use for Phasing & Construction
3D Coordination (Construction) | HIGH | Contractor | HIGH | 3 | 3 | 3 |  |  | YES
|  | Subcontractors | HIGH | 1 | 3 | 3 | conversion to Digital Fab required | Modeling learning curve possible
|  | Designer | MED | 2 | 3 | 3
Engineering Analysis | HIGH | MEP Engineer | HIGH | 2 | 2 | 2 |  |  | MAYBE
|  | Architect | MED | 2 | 2 | 2
Design Reviews | MED | Arch | LOW | 1 | 2 | 1 |  | Reviews to be from design model | NO
no additioanl detail required
3D Coordination (Design) | HIGH | Architect | HIGH | 2 | 2 | 2 | Coordination software required | Contractor to facilitate Coord. | YES
|  | MEP Engineer | MED | 2 | 2 | 1
|  | Structural Engineer | HIGH | 2 | 2 | 1
Design Authoring | HIGH | Architect | HIGH | 3 | 3 | 3 |  |  | YES
|  | MEP Engineer | MED | 3 | 3 | 3
|  | Structural Engineer | HIGH | 3 | 3 | 3
|  | Civil Engineer | LOW | 2 | 1 | 1 | Large learning curve | Civil not required
Programming | MED | [6 empty] | Planning Phase Complete | NO
* Additional information on each BIM Use can be found at http://bim.psu.edu or via the direct link by selecting each use