## Intro
Construction Robotics Planning Template | The Pennsylvania State University
INTRODUCTION
This template complements that Construction Robotics Planning Guide. The template is organized into worksheets for the steps contained within the guideline document.
Template Sections
Goals
Table with Element Breakdown
Robotics List
Identify Robotics Worksheet
Implementation Plan Development Sheet
Robotics Evaluation Framework
Cost Evaluation Worksheet
Choosing By Advantages Worksheet
Risk Registry Worksheet
Performance Tracking Worksheet
References
Brosque, C., Skeie, G., Örn, J., Jacobson, J., Lau, T., & Fischer, M. (2020). Comparison of Construction Robots and Traditional Methods for Drilling, Drywall, and Layout Tasks. 2020 International Congress on Human-Computer Interaction, Optimization and Robotic Applications (HORA), 1–14. https://doi.org/10.1109/HORA49412.2020.9152871 |  | Robotics Evaluation Framework

## Goals(rev1,ex)
PROJECT GOALS
Instructions: Complete the table with the core stakeholders who may need coordination for the implementation of robotic solutions on the project. Set Goals based on stakeholders' expectations.
Stakeholders Expectation and Influence
Stakeholder | Internal/ External | Expectations of using robotics | Impact to other stakeholders | Remark | Goals
Owner: A | Internal | Not concerned about it unless project complete schedule to be on time | Possibly deny using robotics if project team can't meet project schedule |  | Higher productivity with a reliable schedule by smooth coordination
GC: B construction | Internal | Desire reliable schedule due to tight schedule | Coordination between C company and D construction is required
Trade: C company | Internal | Higher production with less manhours | Need coordination with D construstion | Want to bring robotics C company ownes
Trade: D construction | Internal | Don't want to see production of D construction going down | Possibly argue C company using robotics if C company offensively disturb or add work to D construction
Adjacent building owner | External | Less sound from the project | Possibly deny using robotics if project team is making more noise by using robotics
Add rows as needed.

## Goals(rev1)
PROJECT GOALS
Instructions: Complete the table with the core stakeholders who may need coordination for the implementation of robotic solutions on the project. Set Goals based on stakeholders' expectations.
Stakeholders Expectation and Influence
Stakeholder | Internal/ External | Expectations of using robotics | Impact to other stakeholders | Remark | Goals
Add rows as needed.

## Table with Element Breakdown
TASK BREAKDOWN FOR CONSIDERING ROBOTICS - OMNICLASS TABLE 21- BUILDINGS
Instructions: This table includes all scopes of work for a typical building project that may be able to benefit from the use of robotics. This is provided to consider potential robotic tasks. For consider, include Y = Yes, N = No, and M = Maybe.
Potential Robot Solutions
OmniClass Table 21 to Level 3 (All Numbers Start with 21 for Table 21) |  |  |  | Consider (Y ¦ N ¦ M) | Potential Robots | Notes
01 | SUBSTRUCTURE
01 | 10 | Foundations
01 | 10 | 10 | Standard Foundations
01 | 10 | 20 | Special Foundations
01 | 20 | Subgrade Enclosures
01 | 20 | 10 | Walls for Subgrade Enclosures
01 | 40 | Slabs-on-Grade
01 | 40 | 10 | Standard Slabs-on-Grade
01 | 40 | 20 | Structural Slabs-on-Grade
01 | 40 | 20 | Slab Trenches
01 | 40 | 20 | Pits and Bases
01 | 40 | 20 | Slab-on-Grade Supplementary Components
01 | 60 | Water and Gas Mitigation
01 | 60 | 10 | Building Subdrainage
01 | 60 | 20 | Off-Gassing Mitigation
01 | 90 | Substructure Related Activities
01 | 90 | 10 | Substructure Excavation
01 | 90 | 20 | Construction Dewatering
01 | 90 | 20 | Excavation Support
01 | 90 | 20 | Soil Treatment
02 | SHELL
02 | 10 | Superstructure
02 | 10 | 10 | Floor Construction
02 | 10 | 20 | Roof Construction
02 | 10 | 80 | Stairs
02 | 20 | Exterior Vertical Enclosures
02 | 20 | 10 | Exterior Walls
02 | 20 | 20 | Exterior Windows
02 | 20 | 50 | Exterior Doors and Grilles
02 | 20 | 70 | Exterior Louvers and Vents
02 | 20 | 80 | Exterior Wall Appurtenances
02 | 20 | 90 | Exterior Wall Specialties
02 | 30 | Exterior Horizontal Enclosures
02 | 30 | 10 | Roofing
02 | 30 | 20 | Roof Appurtenances
02 | 30 | 40 | Traffic Bearing Horizontal Enclosures
02 | 30 | 60 | Horizontal Openings
02 | 30 | 80 | Overhead Exterior Enclosures
03 | Interiors
03 | 10 | Interior Construction
03 | 10 | 10 | Interior Partitions
03 | 10 | 20 | Interior Windows (a.k.a. borrowed lites)
03 | 10 | 30 | Interior Doors
03 | 10 | 40 | Intereior Grills and Gates
03 | 10 | 60 | Raised Floor Construction
03 | 10 | 70 | Suspended Ceiling Construction
03 | 10 | 90 | Interior Specialties
03 | 20 | Interior Finishes
03 | 20 | 10 | Wall Finishes
03 | 20 | 20 | Interior Fabrications
03 | 20 | 30 | Flooring
03 | 20 | 40 | Stair Finishes
03 | 20 | 50 | Ceiling Finishes
04 | Services
04 | 10 | Conveying
04 | 10 | 10 | Vertical Conveying Systems
04 | 10 | 30 | Horizontal Conveying Systems
04 | 10 | 50 | Material Handling
04 | 10 | 80 | Operable Access Systems
04 | 20 | Plumbing
04 | 20 | 10 | Domestic Water Distribution
04 | 20 | 20 | Sanitary Drainage
04 | 20 | 30 | Building Support Plumbing Systems
04 | 20 | 50 | General Service Compressed-Air
04 | 20 | 60 | Process Support Plumbing Systems
04 | 30 | HVAC
04 | 30 | 10 | Facility Fuel Systems
04 | 30 | 20 | Heating Systems
04 | 30 | 30 | Cooling Systems
04 | 30 | 50 | Facilitiy HVAC Distribution Systems
04 | 30 | 60 | Ventilation
04 | 30 | 70 | Special Purpose HVAC Systems
04 | 40 | Fire Protection
04 | 40 | 10 | Fire Suppression
04 | 40 | 20 | Fire Protection Specialties
04 | 50 | Electrical
04 | 50 | 10 | Facility Power Generation
04 | 50 | 20 | Electrical Service and Distribution
04 | 50 | 30 | General Purpose Electrical Power
04 | 50 | 40 | Lighting
04 | 50 | 80 | Miscellaneous Electrical Systems
04 | 60 | Communications
04 | 60 | 10 | Data Communications
04 | 60 | 20 | Voice Communications
04 | 60 | 30 | Audio-Video Communication
04 | 60 | 60 | Distributed Communications and Monitoring
04 | 60 | 90 | Communications Supplementary Components
04 | 70 | Electronic Safety and Security
04 | 70 | 10 | Access Control and Intrusion Detection
04 | 70 | 30 | Electronic Surveillance
04 | 70 | 50 | Detection and Alarm
04 | 70 | 70 | Electronic Monitoring and Control
04 | 70 | 90 | Electronic Safety and Security Supplementary Components
04 | 80 | Integrated Automation
04 | 80 | 10 | Integrated Automation Facility Controls
05 | Equipment and Furnishings
05 | 10 | Equipment
05 | 10 | 10 | Vehicle and Pedestrian Equipment
05 | 10 | 30 | Commercial Equipment
05 | 10 | 40 | Institutional Equipment
05 | 10 | 60 | Residential Equipment
05 | 10 | 70 | Entertainment and Recreational Equipment
05 | 10 | 90 | Other Equipment
05 | 20 | Furnishings
05 | 20 | 10 | Fixed Furnishings
05 | 20 | 50 | Movable Furnishings
06 | Special Construction and Demolition
06 | 10 | Special Construction
06 | 10 | 10 | Integrated Construction
06 | 10 | 20 | Special Structures
06 | 10 | 30 | Special Function Construction
06 | 10 | 50 | Special Facility Components
06 | 10 | 60 | Athletic and Recreational Special Construction
06 | 10 | 80 | Special Instrumentation
06 | 20 | Facility Remediation
06 | 20 | 10 | Hazardous Materials and Remediation
06 | 30 | Demolition
06 | 30 | 10 | Structural Demolition
06 | 30 | 30 | Selective Demolition
06 | 30 | 50 | Structure Moving
07 | Sitework
07 | 10 | Site Preparations
07 | 10 | 10 | Site Clearing
07 | 10 | 20 | Site Elements Demolition
07 | 10 | 30 | Site Elements Relocations
07 | 10 | 50 | Site Remediation
07 | 10 | 70 | Site Earthwork
07 | 20 | Site Improvements
07 | 20 | 10 | Roadways
07 | 20 | 20 | Parking Lots
07 | 20 | 30 | Pedestrian Plazas and Walkways
07 | 20 | 40 | Airfields
07 | 20 | 50 | Athletic, Recreational, and Playfield Areas
07 | 20 | 60 | Site Development
07 | 20 | 80 | Landscaping
07 | 30 | Liquid and Gas Site Utilities
07 | 30 | 10 | Water Utilities
07 | 30 | 20 | Sanitary Sewerage Utilities
07 | 30 | 30 | Storm Drainage Utilities
07 | 30 | 50 | Site Energy Distribution
07 | 30 | 60 | Site Fuel Distribution
07 | 30 | 90 | Liquid and Gas Site Utiliities Supplementatry Components
07 | 40 | Electrical Site Improvements
07 | 40 | 10 | Site Electric Distibution Systems
07 | 40 | 50 | Site Lighting
07 | 50 | Site Communications
07 | 50 | 10 | Site Communications Systems
07 | 90 | Miscellaneous Site Construction
07 | 90 | 10 | Tunnels
Layout
Scaffolding
Etc. - ITEMS NOT IN OMNICLASS

## Robotics List
LIST OF POTENTIAL CONSTRUCTION ROBOTICS BY OMNICLASS TABLE 21
Instructions: This is a list of potential robot solutions. Refer to omniclass activity to spot applicable robotics. (under development)
Construction Robots
Robot Name | Website | Image | Omniclass Table 21 or Additional Activity | Notes
Dusty | https://www.dustyrobotics.com/ | https://www.dustyrobotics.com/ | Layout
Rugged | https://rugged-robotics.com/ | https://rugged-robotics.com/ | Layout
HP SitePrint | https://www.hp.com/us-en/printers/site-print/layout-robot.html | https://www.hp.com/us-en/printers/site-print/layout-robot.html | Layout
Canvas | https://www.canvas.build/ | https://www.canvas.build/ | 03 10 10 Interior Partitions | Drywall finishing.
Okibo | https://okibo.com/ | https://okibo.com/ | 03 10 10 Interior Partitions | Drywall finishing.
Toggle | https://toggle.is/ | https://toggle.is/ | 01 40 20 Structural Slab On Grade 02 10 10 Floor construction, etc. | Fabricate rebar cage by robotics off-site and transport to sites.
Civ-Robotics | https://www.civrobotics.com/ | https://www.civrobotics.com/ | Layout(outdoor)
Tiny Surveyor | https://www.monsenengineering.com/survey/tinysurveyor/ | https://www.monsenengineering.com/survey/tinysurveyor/ | Layout(outdoor)
Raise Robotics | https://raiserobotics.ai | https://raiserobotics.ai/portfolio/ | 02 20 10 Exterior Walls | Mostly for installing anchors for curtain walls.

## Identify Robot Solutions
IDENTIFY ROBOTIC SOLUTIONS
Instructions: This table is to identify potential robotics solutions that align with the goals in the end. First, analyze the constraints or concerns to achieve the goal. Then, pick the construction tasks from the structured list of tasks with features ideal for robotics implementation. Next, pick potential robotics that has the potential to be implemented in the project.
Indentification of Robotic Solutions
Goal | Constraints / Areas of Concern | Features | Tasks | Robotics
Add rows as needed.

## Identify Robot Solutions (ex)
IDENTIFY ROBOTIC SOLUTIONS
Instructions: This table is to identify potential robotics solutions that align with the goals in the end. First, analyze the constraints or concerns to achieve the goal. Then, pick the construction tasks from the structured list of tasks with features ideal for robotics implementation. Next, pick potential robotics that has the potential to be implemented in the project.
Indentification of Robotic Solutions
Goal | Constraints / Areas of Concern | Features | Tasks | Robotics
On time Schedule with high productivity | Lack of Workforce | • Repetitive • High volume | 03 20 10 Wall Finishes | Canvas, Okibo
On time Schedule with high productivity | Lack of Workforce | • High accuracy demand • Ergonomic challenge | 03 10 Interior Construction (Layout) | Dusty, Rugged, SitePrint
Minimum safety incidents | Height | • Hazardous • Standardized process | 02 20 10 Exterior walls (Curtain walls) | RAISE robotics
Add rows as needed.

## Implementation Plan Development
Implementation Plan Development Worksheet
Instructions: This table is to develop an inplementation plan for each robotics that has been identified in earlier step. Feasibility, Schedule, Site Logistics, Additional Resource, On-boarding are the key components.
Date: |  | Developed by:
Robotics Description
Name of Robotics:
Image of Robotics:
Add discription here.
Feasibility
| Feasible? | Remarks
Product
Organization
Plan
Schedule
Schedule Related
Related Milestone Date
Predecessor Activity
Set Up Time
Estimated Start Day
Estimated Workday by Robotics
Estimated End Day
Successor Activity
Site Logistics
Draw a site logistics plan here
Additional Resources
Resource | Purpose | Amount
Material A
Material B
Equipment A
On-Boarding
| Target | Duration
Training

## Robotics Evaluation Framework
Robotics Feasibility Evaluation
Instructions: Complete the table to evaluate the feasibility of robotics.
Robotics Name:
POP |  | Data | Remarks | Feasibility (Y/N)
Product | Single/multi-task
Interior/Exterior
Hardware
Mobility
Autonomy
Controls
Power
Software/senosors
Weight
Clearance
Reach
Materials
Location
Project type
Project area
Organization | # Stakeholders
Stakeholders
Process | Process
Information/QC
*Formatted based on Brosque, C., Skeie, G., Örn, J., Jacobson, J., Lau, T., & Fischer, M. (2020). Comparison of Construction Robots and Traditional Methods for Drilling, Drywall, and Layout Tasks. 2020 International Congress on Human-Computer Interaction, Optimization and Robotic Applications (HORA), 1–14. https://doi.org/10.1109/HORA49412.2020.9152871

## Cost Evaluation
Cost Evaluation
Instructions: Compare the cost of robotics implementation and the traditional construction method.
Cost Type | Traditional Method |  |  |  | Robotics A
Labor | Unit Price | Number | Duration | Total | Unit Price | Number | Duration | Total
| 0 |  |  | 0 | 0 |  |  | 0
Equipment | Unit Price | Number | Duration | Total | Unit Price | Number | Duration | Total
| 0 |  |  | 0 | 0 |  |  | 0
Direct Robotics Fee | N/A |  |  |  | Unit Price | Number | Duration | Total
[5 empty] | 0 |  |  | 0
Associated Robotics Fee | N/A |  |  |  | 0
Robotics Maintenance | N/A |  |  |  | 0
Transportation/Relocation | N/A |  |  |  | 0
other | 0 |  |  |  | 0
Total | 0 |  |  |  | 0

## Cost Evaluation(ex)
Cost Evaluation
Instructions: Compare the cost of robotics implementation and the traditional construction method.
Cost Type | Traditional Method |  |  |  | Robotics A
Labor | Unit Price | Number | Duration | Total | Unit Price | Number | Duration | Total
| 350 | 4 | 15 | 21000 | 350 | 1 | 3 | 1050
Equipment | Unit Price | Number | Duration | Total | Unit Price | Number | Duration | Total
| 200 | 1 | 15 | 3000 | 0 | 0 | 0 | 0
Direct Robotics Fee | N/A |  |  |  | Unit Price | Number | Duration | Total
[5 empty] | 2000 | 1 | 5 | 10000
Associated Robotics Fee | N/A |  |  |  | 5000
Robotics Maintenance | N/A |  |  |  | 500
Transportation/Relocation | N/A |  |  |  | 500
other | 0 |  |  |  | 0
Total | 24000 |  |  |  | 17050

## Choosing-By-Advantage
Choosing By Advantages
Instructions: First, determine the desired attributes necessary for each of the factors. Decide how each option based on those desired attributes. Instructions: Then, rank each of the factors based on priority and importance. Score each method based on how well it aligns with the desired attributes of the factor. Cost should be considered separately from the advantages.
Factors | Must-Haves / Want-to-Have (Desired Attributes) | Ranking by Priority and Importantance | Assign Attribute Weight | Option A Score | Option B Score
|  |  | Total Score | 0 | 0
Cost |  |  |  | 0 | 0

## CBA(ex)
Choosing By Advantages
Instructions: First, determine the desired attributes necessary for each of the factors. Decide how each option based on those desired attributes. Instructions: Then, rank each of the factors based on priority and importance. Score each method based on how well it aligns with the desired attributes of the factor. Cost should be considered separately from the advantages.
Factors | Must-Haves / Want-to-Have (Desired Attributes) | Ranking by Priority and Importantance | Assign Attribute Weight | Option A Score | Option B Score
Safety | No height work | 1 | 5 |  | 5
Productivity | Fast completion | 3 | 3 | 3
Quality | Less rework with high accuracy work | 2 | 4 |  | 4
Sustainability | Less waste | 4 | 2 | 2
|  |  | Total Score | 5 | 9
Cost |  |  |  | 18000 | 24000

## Risk Reg
RISK REGISTRY
Instruction: Evaluate risks for robotics and traditional methods.
Risk Title | Description | Probability | Consequence | Mitigation Methods | Category | Status | Resp. Party
Add rows as needed.

## Performance Tracking Template
Construction Robotics Performance Tracking
Instructions: This table is to track the performance of robotics implementation. It is to have feedback and create PDCA cycle for better implementation.
Date:
Metric | Criteria | Target | Actual | Variance | Comments/Notes
Labor Effects
Robot Performance
Efficiency
Safety
Production
Productivity
Cost
Schedule
Quality
Other
Overall Notes:

## Project Information (hidden)
BIM Execution Plan (BEP) - Project Information
Project Reference Information
Project Name
Project Owner Name
Project Legal Address
Project Description
Project Delivery Method
Owner Modeling Guide Title
Owner Modeling Guide Location
Asset Information Requirements
Facility Type Classification
Facility Type Name
Project Certification Information
Certification Information
Certification Value
Project Identification Table
Project Identification Description
Project Identification Value
Project Metrics Value
Project Metrics Name
Project Metrics Value
Project Metrics Unit
BIM Contacts
Organization
Organization Name
Abbreviation
Phone Number
Office Location
Organization Role
Contact
Organization
Contact Name
Contact Role
Email Address
Phone Number
Primary Location
Executive Summary
Summary
Organizational Roles and Responsibilities
BIM Roles
Role Name
Role Description
Role Responsibility
Required by Contract
Role Code

## BEP Metadata (CC) (hidden)
BIM Execution Plan (BEP) - BEP Metadata
BEP Metadata and Clarifications | Color Coding Key
BEP URL | Required By | Color
BEP Data Format | Owner
Approval Status | Proposer
BEP Standard Use for Development | Team
Approval/Organization Contact | Optional
Acknowledgements
BEP Version Log
BEP Version Nubmer
BEP Version Date
BEP Version Description
BEP Version Creator

## Project Goals and Milestones (hidden)
BIM Execution Plan (BEP) - Project Goals and Milestones
Project Milestones
Project Phases
Phase Name
Phase Description
Estimated Start Date
Estimated Completion Date
Actual Start Date
Actual Completion Date
Project Milestones
Milestone Name
Milestone Description
Estimated Date
Actual Date
Phase
Project Goals
Project Goals
Goal Description
Priority
Potential BIM Uses to Support Goal
Goal Customer
Goal Primary Responsible Party
Constraints
Goal Phase